## 348388
Package :-e-GP-03/ADP/DRW-03/Sangu/2019-20 |  | WORK SCHEDULE | [6 empty] | Tender ID: 348388
Name of Work: "Capital Dredging of Sangu River at different locations in between KM 33.500 to KM 41.832 8.332 km in Upazila-Satkania Dist Chattogram during the year 2019-2020."
Sl. No. | Activity | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020
Sl. No. | Activity | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
i | Site Preparation & Mobilization.
ii | Procurement of Man power, Equipment, Materials & etc.
iii | E/W in excavation/re-excavation of khal & foundation trench etc.
iv | Manufacturing of C.C. Blocks
v | Supply of Sand Filter, Geo-Textile Filter, Khoa filter etc.
vi | Dumping & Placing C.C Blocks
vii | Construction Of Herring Bone Bond (HBB) Brick Road.
viii | Supplying, Filling & Laying Geo-Tube
ix | Fine dressing and close turfing of the slopes and the crest of embankment
x | De-mobilization & Site handover