## 585452
Package :-DCP-Bor-RBP-08 |  | WORK SCHEDULE | [6 empty] | Tender ID: 585452
Name of Work: "Bank Protection work from km 44.650 to km 44.800 equal to 0.150 km in connection with "Protection of Daulatkhan Pourashava, Chokighat and other more vulnerable area from the erosion of the Meghna river in Bhola District" project under Bhola O&M Division-I, BWDB, Bhola."
Sl. No. | Activity | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022
Sl. No. | Activity | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
i | Site Preparation & Mobilization.
ii | Procurement of Man power, Equipment, Materials & etc.
iii | E/W in excavation/re-excavation of khal & foundation trench etc.
iv | Manufacturing of C.C. Blocks
v | Supply of Sand Filter, Geo-Textile Filter, Khoa filter etc.
vi | Dumping & Placing C.C Blocks
vii | Construction Of Herring Bone Bond (HBB) Brick Road.
viii | Supplying, Filling & Laying Geo-Tube
ix | Fine dressing and close turfing of the slopes and the crest of embankment
x | De-mobilization & Site handover